## Sheet1
| To Do |  | Done?
Apr 15-21 |  | A
Jordan | Implement periodicity and metagene sub-modules | A | Done
Jordan | Finish preliminary test cases | A
Jordan | Prep for shipping to 1st round testers | A
Jordan | Prep BioRXiv manuscript for review | A
Apr 22-28 |  | A
| Jordan in China | A
Authors | Authors review BioRXiv manuscript | A
Testers | Have 1st round testers test pipelines | A
Jon | Have Jon write test cases for rRNAprobe | A
Apr 29-May 5 |  | A
Jordan | Test cases | A
Jordan | Solidify documentation | A
Jordan | Write tester soliciation for dept users
Jared | Get RNAseq future users committed from dept | A
Users | Future users do preliminary training | A
Authors | Revise BioRXiv manuscript
May 6 - 12 |  | A
Jordan | Test cases | A
Jordan | Solidify documentation | A
Users | Future users do preliminary training | A
Authors | Revise BioRXiv manuscript
May 13-19 |  | A
Jordan | Create video walkthroughs | A
Jordan | Biological analysis | A
Users | CASE STUDY: Test pipeline ease of use | A
Authors | Revise BioRXiv manuscript
May 20-26 |  | A
Jordan | Biological analysis | A
Users | CASE STUDY: Test pipeline ease of use | A
Authors | Submit BioRXiv (incorporate case study) | A
May 27-June 2 |  | A
Jordan | Biological analysis | A
June 3-9 |  | A
Jordan | Biological analysis | A
Jordan | Incorporate biological analysis into manuscript | A
June 10-16 |  | A
Jordan | Biological analysis | A
Jordan | Incorporate biological analysis into manuscript | A
Authors | Submit to journal | A
June 17- |  | A
Jordan | Get preliminary data for F31/F99 | A